## Instructions
Self-Assessment
All levels, all domains
Please support our commitment to sustainability and do not print
this document unless it is absolutely necessary to do so.
1. General Information
Purpose | The primary purpose of this form is to encourage applicants to become familiar with the content of the ICB.
Questions or Problems? | If you have questions or problems, contact us at:
Cert-Operations@IPMA-USA.org
This document was designed by IPMA-USA for use in its certification program. The design of this document is licensed for use by others under the Creative Commons Attribution 4.0 International License. For a copy of that license, visit:
http://creativecommons.org/licenses/by/4.0/
Content in dark blue is not included in the license.
Movement Between Cells | Use your TAB key to move to the next available entry field.
Manual Entry Fields | Manual entry fields are shaded gray (like this cell).
Menu Entry Fields | Menu entry fields are shaded light yellow (like this cell).
Basis of Assessment | The IPMA Individual Competence Baseline (IPMA ICB) describes the competence elements that will be used to assess your competence. If you are not already familiar with the ICB, you should review it prior to continuing with the application process. You can download a free copy as follows:
• Go to https://shop.ipma.world/ • Click on the link to purchase the hard copy version • Click on the link to download the free e-Book
2. Level A, B, and C Applicants
Name, Level, and Domain | Enter your name at the top of the Levels A, B, and C worksheet. Enter the level and domain you are applying for if that differs from the default (default is Level C and Project Management domain).
Skills and Abilities | Follow the instructions on the worksheet.
Notes, Comments, Evidence | The column headed "Notes, comments, evidence" is for your use. It is often used to record reasons for unusual scores, or to record reminders of evidence sources. However, it can be left blank.
3. Level D Applicants
Name | Enter your name at the top of the Level D worksheet.
Knowledge | Follow the instructions on the worksheet.
Notes, Comments, Evidence | The column headed "Notes, comments, evidence" is for your use. It is often used to record reasons for unusual scores, or to record reminders of evidence sources. However, it can be left blank.
4. Project, Program, and Portfolio Scores (Levels A, B, and C only)
Use | These worksheets are for your use and are 100% optional.
Purpose | These worksheets serve two purposes: • If you are unsure about how to score your strengths and weaknesses, they may provide insight into what criteria to consider. • They may provide insight into how your actual assessment might be scored by your assessors.
Content | These worksheets use the Key Competence Indicators (KCIs) for each Competence Element in the ICB. The KCIs are scored to assess competence for Level A, B, and C candidates.
Pass or Fail | A competence element will show as "Pass" if you score at least 50% of the KCIs 2 or 3.
version 4.1

## Levels A, B, and C
Self-Assessment |  | Candidate Name: |  |  | Level: | C | Domain: | Project
Levels A, B, and C
Identify the 6-8 competence elements where you feel you are strongest. Enter an "S" in those cells. Identify the 6-8 competence elements where you feel you are weakest. Enter a "W" in those cells. There are no right or wrong ratings. Use your own best judgment.
Competence Elements |  | Skills & Abilities (A, B, C) |  | Notes, comments, evidence (optional; for candidate use)
Overall | Strengths
Weaknesses
Perspective Competence Elements
4.3.1 | Strategy | [7 empty] | 1
4.3.2 | Governance, structures, and processes | [7 empty] | 2
4.3.3 | Compliance, standards, and regulations | [7 empty] | 3
4.3.4 | Power and interest | [7 empty] | 4
4.3.5 | Culture and values | [7 empty] | 5
Number of strengths
Number of weaknesses
Personal Competence Elements
4.4.1 | Self-reflection and self-management | [7 empty] | 1
4.4.2 | Personal integrity and reliability | [7 empty] | 2
4.4.3 | Personal communication | [7 empty] | 3
4.4.4 | Relations and engagement | [7 empty] | 4
4.4.5 | Leadership | [7 empty] | 5
4.4.6 | Teamwork | [7 empty] | 6
4.4.7 | Conflict and crisis | [7 empty] | 7
4.4.8 | Resourcefulness | [7 empty] | 8
4.4.9 | Negotiation | [7 empty] | 9
4.4.10 | Results orientation | [7 empty] | 10
Number of strengths
Number of weaknesses
Practice Competence Elements
4.5.1 | Project design | [7 empty] | 1
4.5.2 | Requirements and objectives | [7 empty] | 2
4.5.3 | Scope | [7 empty] | 3
4.5.4 | Time | [7 empty] | 4
4.5.5 | Organization and information | [7 empty] | 5
4.5.6 | Quality | [7 empty] | 6
4.5.7 | Finance | [7 empty] | 7
4.5.8 | Resources | [7 empty] | 8
4.5.9 | Procurement | [7 empty] | 9
4.5.10 | Plan and control | [7 empty] | 10
4.5.11 | Risk and opportunity | [7 empty] | 11
4.5.12 | Stakeholders | [7 empty] | 12
4.5.13 | Change and transformation | [7 empty] | 13
4.5.14 | Select and balance | [7 empty] | 14
Number of strengths
Number of weaknesses
Summary Counts
Perspective Competence Elements
Strengths
Weaknesses
Personal Competence Elements
Strengths
Weaknesses
Practice Competence Elements
Strengths
Weaknesses
Overall
Strengths
Weaknesses
Note: Self-Assessment scores are for information only
version 4.1
4
28

## Level D
Self-Assessment |  | Candidate Name: |  |  | Level: | D | Domain: | Project
Candidate Scores: Level D
Identify the 6-8 competence elements where you feel you are strongest. Enter an "S" in those cells. Identify the 6-8 competence elements where you feel you are weakest. Enter a "W" in those cells. There are no right or wrong ratings. Use your own best judgment.
Competence Elements |  | Knowledge |  | Notes, comments, evidence (optional; for candidate use)
Overall | Strengths
Weaknesses
Perspective Competence Elements
4.3.1 | Strategy | [7 empty] | 1
4.3.2 | Governance, structures, and processes | [7 empty] | 2
4.3.3 | Compliance, standards, and regulations | [7 empty] | 3
4.3.4 | Power and interest | [7 empty] | 4
4.3.5 | Culture and values | [7 empty] | 5
Number of strengths
Number of weaknesses
Personal Competence Elements
4.4.1 | Self-reflection and self-management | [7 empty] | 1
4.4.2 | Personal integrity and reliability | [7 empty] | 2
4.4.3 | Personal communication | [7 empty] | 3
4.4.4 | Relations and engagement | [7 empty] | 4
4.4.5 | Leadership | [7 empty] | 5
4.4.6 | Teamwork | [7 empty] | 6
4.4.7 | Conflict and crisis | [7 empty] | 7
4.4.8 | Resourcefulness | [7 empty] | 8
4.4.9 | Negotiation | [7 empty] | 9
4.4.10 | Results orientation | [7 empty] | 10
Number of strengths
Number of weaknesses
Practice Competence Elements
4.5.1 | Project design | [7 empty] | 1
4.5.2 | Benefits and objectives | [7 empty] | 2
4.5.3 | Scope | [7 empty] | 3
4.5.4 | Time | [7 empty] | 4
4.5.5 | Organization and information | [7 empty] | 5
4.5.6 | Quality | [7 empty] | 6
4.5.7 | Finance | [7 empty] | 7
4.5.8 | Resources | [7 empty] | 8
4.5.9 | Procurement | [7 empty] | 9
4.5.10 | Plan and control | [7 empty] | 10
4.5.11 | Risk and opportunity | [7 empty] | 11
4.5.12 | Stakeholders | [7 empty] | 12
4.5.13 | Change and transformation | [7 empty] | 13
Number of strengths
Number of weaknesses
Summary Counts
Perspective Competence Elements
Strengths
Weaknesses
Personal Competence Elements
Strengths
Weaknesses
Practice Competence Elements
Strengths
Weaknesses
Overall
Strengths
Weaknesses
Note: Self-Assessment scores are for information only
version 4.1
4
28

## Project Scores
| Detail Self-Assessment Project Domain |  | Rate the level of your agreement with the following statement:
I can provide clear and convincing evidence of my Skills and Abilities in the
indicated KCI from a project of sufficient complexity for the level applied for.
Blank = Disagree or no evidence; 1 = Not sure; 2 = Agree; 3 = Strongly agree
|  | S&A |  | Notes, comments, and evidence
Perspective Competence Elements
4.3.1 | Strategy |  |  |  | 5 | 3 | Converted spelling and punctuation to US English
.1 | Align with organizational mission and vision
.2 | Identify and exploit opportunities to influence organizational strategy
.3 | Develop and ensure the ongoing validity of the business/organizational justification
.4 | Determine, assess, and review critical success factors
.5 | Determine, assess, and review key performance indicators
4.3.2 | Governance, structures, and processes |  |  |  | 5 | 3 | Removed need to 'know and apply program and portfolio'
.1 | Know the principles of project management and the way they are implemented
.2 | Align the project with the project supporting function
.3 | Align the project with the organization's decision making, reporting structures, and quality requirements
.4 | Align the project with the organization's human resource processes and functions
.5 | Align the project with the organization's finance and control processes and functions
4.3.3 | Compliance, standards, and regulations |  |  |  | 6 | 3 | Modified punctuation
.1 | Identify, and ensure that the project complies with, all relevant legislation
.2 | Identify, and ensure that the project complies with, all relevant health, safety, security, and environmental regulations (HSSE)
.3 | Identify, and ensure that the project complies with, all relevant codes of conduct and professional regulation
.4 | Identify, and ensure that the project complies with, relevant sustainability principles and objectives
.5 | Assess, use, and develop professional standards and tools for the project
.6 | Assess, benchmark, and improve the organization's project management competence | [5 empty] | Changed "organizational" to "organization's" for consistency
4.3.4 | Power and interest |  |  |  | 3 | 2
.1 | Assess the personal ambitions and interests of others and the potential impact of these on the project
.2 | Assess the informal influence of individuals and groups and its potential impact on the project
.3 | Assess the personalities and working styles of others and employ them to the benefit of the project
4.3.5 | Culture and values |  |  |  | 3 | 2
.1 | Assess the culture and values of society and their implications for the project
.2 | Align the project with the formal culture and values of the organization
.3 | Assess the informal culture and values of the organization and their implications for the project
Personal Competence Elements
4.4.1 | Self-reflection and self-management |  |  |  | 5 | 3
.1 | Identify, and reflect on, the ways in which one's own values and experiences affect the work
.2 | Build self-confidence on the basis of personal strengths and weaknesses
.3 | Identify, and reflect on, personal motivations to set personal goals and keep focus
.4 | Organize personal work depending on the situation and one's own resources
.5 | Take responsibility for personal learning and development
4.4.2 | Personal integrity and reliability |  |  |  | 5 | 3
.1 | Acknowledge and apply ethical values to all decisions and actions
.2 | Promote the sustainability of outputs and outcomes
.3 | Take responsibility for one's own decisions and actions
.4 | Act, take decisions, and communicate in a consistent way
.5 | Complete tasks thoroughly in order to build confidence with others
4.4.3 | Personal communication |  |  |  | 5 | 3
.1 | Provide clear and structured information to others and verify their understanding
.2 | Facilitate and promote open communication
.3 | Choose communication styles and channels to meet the needs of the audience, situation, and management level
.4 | Communicate effectively with virtual teams
.5 | Employ humor and sense of perspective when appropriate
4.4.4 | Relations and engagement |  |  |  | 5 | 3
.1 | Initiate and develop personal and professional relations
.2 | Build, facilitate, and contribute to social networks
.3 | Demonstrate empathy through listening, understanding, and support
.4 | Show confidence and respect by encouraging others to share their opinions or concerns
.5 | Share one's own vision and goals in order to gain the engagement and commitment of others
4.4.5 | Leadership |  |  |  | 5 | 3
.1 | Initiate actions and proactively offer help and advice
.2 | Take ownership and show commitment
.3 | Provide direction, coaching, and mentoring to guide and improve the work of individuals and teams
.4 | Exert appropriate power and influence over others to achieve project goals | [5 empty] | Changed "the" to "project"
.5 | Make, enforce, and review decisions
4.4.6 | Teamwork |  |  |  | 5 | 3
.1 | Select and build the team
.2 | Promote cooperation and networking between team members
.3 | Support, facilitate, and review the development of the team and its members
.4 | Empower teams by delegating tasks and responsibilities
.5 | Recognize errors to facilitate learning from mistakes
4.4.7 | Conflict and crisis |  |  |  | 4 | 2
.1 | Anticipate and possibly prevent conflicts and crises
.2 | Analyze the causes and consequences of conflicts and crises and select appropriate response(s)
.3 | Mediate and resolve conflicts and crises and/or their impact
.4 | Identify and share learning from conflicts and crises in order to improve future practice
4.4.8 | Resourcefulness |  |  |  | 5 | 3
.1 | Stimulate and support an open and creative environment
.2 | Apply conceptual thinking to define situations and strategies
.3 | Apply analytic techniques to analyzing situations and financial and organizational data and trends | [5 empty] | Corrected grammar
.4 | Promote and apply creative techniques to find alternatives and solutions
.5 | Promote a holistic view of the project and its context to improve decision-making
4.4.9 | Negotiation |  |  |  | 5 | 3
.1 | Identify and analyze the interests of all parties involved in the negotiation
.2 | Develop and evaluate options and alternatives with the potential to meet the needs of all parties
.3 | Define a negotiation strategy in line with one's own objectives that is acceptable to all parties involved
.4 | Reach negotiated agreements with other parties that are in line with one's own objectives
.5 | Detect and exploit additional selling and acquisition possibilities
4.4.10 | Results orientation |  |  |  | 5 | 3
.1 | Evaluate all decisions and actions against their impact on project success and the objectives of the organization
.2 | Balance needs and means to optimize outcomes and success
.3 | Create and maintain a healthy, safe, and productive working environment
.4 | Promote and 'sell' the project and its processes and outcomes
.5 | Deliver results and get acceptance
Practice Competence Elements
4.5.1 | Project design |  |  |  | 5 | 3
.1 | Acknowledge, prioritize, and review success criteria
.2 | Review, apply, and exchange lessons learned from and with other projects
.3 | Determine complexity and its consequences for the approach
.4 | Select and review the overall project management approach
.5 | Design the project execution architecture
4.5.2 | Requirements and objectives |  |  |  | 3 | 2
.1 | Define and develop the project goal hierarchy
.2 | Identify and analyze project stakeholder needs and requirements
.3 | Prioritize and decide on requirements and acceptance criteria
4.5.3 | Scope |  |  |  | 4 | 2
.1 | Define the project deliverables
.2 | Structure the project scope
.3 | Define the work packages of the project
.4 | Establish and maintain scope configuration
4.5.4 | Time |  |  |  | 5 | 3
.1 | Define the activities required to deliver the project
.2 | Determine the work effort and duration of activities
.3 | Decide on schedule and phasing approach | [5 empty] | Changed "stage" to "phase"
.4 | Sequence project activities and create a schedule
.5 | Monitor progress against the schedule and make any necessary adjustments
4.5.5 | Organization and information |  |  |  | 4 | 2
.1 | Assess and determine the needs of stakeholders relating to information and documentation
.2 | Define the structure, roles, and responsibilities within the project
.3 | Establish infrastructure, processes, and systems for information flow
.4 | Implement, monitor, and maintain the organization of the project
4.5.6 | Quality |  |  |  | 5 | 3
.1 | Develop, monitor the implementation of, and maintain a quality management plan for the project | [5 empty] | Changed "revise" to "maintain"
.2 | Review the project and its deliverables to ensure that they continue to meet the requirements of the quality management plan
.3 | Verify the achievement of project quality objectives and recommend any necessary corrective and/or preventive actions
.4 | Plan and organize the validation of project outcomes
.5 | Ensure quality throughout the project
4.5.7 | Finance |  |  |  | 5 | 3
.1 | Estimate project costs
.2 | Establish the project budget
.3 | Secure project funding
.4 | Develop, establish, and maintain a financial management and reporting system for the project
.5 | Monitor project financials in order to identify and correct deviations from the project plan
4.5.8 | Resources |  |  |  | 5 | 3
.1 | Develop a strategic resource plan to deliver the project
.2 | Define the quality and quantity of resources required
.3 | Identify the potential sources of resources, and negotiate their acquisition
.4 | Allocate and distribute resources according to defined need
.5 | Evaluate resource usage and take any necessary corrective actions
4.5.9 | Procurement |  |  |  | 4 | 2
.1 | Agree on procurement needs, options, and processes
.2 | Contribute to the evaluation and selection of suppliers and partners
.3 | Contribute to the negotiation and agreement of contractual terms and conditions that meet project objectives
.4 | Supervise the execution of contracts, address issues, and seek redress where necessary
4.5.10 | Plan and control |  |  |  | 6 | 3
.1 | Start the project, and develop and get agreement on the project management plan
.2 | Initiate and manage the transition to a new project phase
.3 | Control project performance against the project plan and take any necessary corrective actions | [5 empty] | Changed "remedial" to "corrective" for consistency
.4 | Report on project progress
.5 | Assess, get agreement on, and implement project changes
.6 | Close and evaluate a phase or the project
4.5.11 | Risk and opportunity |  |  |  | 5 | 3
.1 | Develop and implement a risk management framework
.2 | Identify risks and opportunities
.3 | Assess the probability and impact of risks and opportunities
.4 | Select strategies and implement response plans to address risks and opportunities
.5 | Evaluate and monitor risks, opportunities, and implemented responses
4.5.12 | Stakeholders |  |  |  | 5 | 3
.1 | Identify stakeholders, and analyze their interests and influence
.2 | Develop and maintain a stakeholder strategy and communication plan
.3 | Engage with the executive, sponsors, and higher management to gain commitment and to manage interests and expectations
.4 | Engage with users, partners, and suppliers to gain their cooperation and commitment
.5 | Organize and maintain networks and alliances
4.5.13 | Change and transformation |  |  |  | 4 | 2
.1 | Assess the adaptability to change of the organization(s)
.2 | Identify change requirements and transformation opportunities
.3 | Develop change or transformation strategy
.4 | Implement change or transformation management strategy
Summary
| Perspective competence elements satisfied | 0
| Personal competence elements satisfied | 0
| Practice competence elements satisfied | 0
Overall result
| Required to pass | 23
version 4.1

## Program Scores
| Detail Self-Assessment Program Domain |  | Rate the level of your agreement with the following statement:
I can provide clear and convincing evidence of my Skills and Abilities
in the indicated KCI from a program of sufficient complexity for the level applied for.
Blank = Disagree or no evidence; 1 = Neutral; 2 = Agree; 3 = Strongly agree
|  | S&A |  | Notes, comments, and evidence
Perspective Competence Elements
5.3.1 | Strategy |  |  |  | 5 | 3 | Converted spelling and punctuation to US English
.1 | Align with organizational mission and vision
.2 | Identify and exploit opportunities to influence organizational strategy
.3 | Develop and ensure the ongoing validity of the business/organizational justification
.4 | Determine, assess, and review critical success factors
.5 | Determine, assess, and review key performance indicators
5.3.2 | Governance, structures, and processes |  |  |  | 5 | 3
.1 | Know the principles of program management and the way they are implemented
.2 | Align the program with the program supporting function
.3 | Align the program with the organization's decision making, reporting structures, and quality requirements
.4 | Align the program with the organization's human resource processes and functions
.5 | Align the program with the organization's finance and control processes and functions
5.3.3 | Compliance, standards, and regulations |  |  |  | 6 | 3
.1 | Identify, and ensure that the program complies with, all relevant legislation
.2 | Identify, and ensure that the program complies with, all relevant health, safety, security, and environmental regulations (HSSE)
.3 | Identify, and ensure that the program complies with, all relevant codes of conduct and professional regulation
.4 | Identify, and ensure that the program complies with, relevant sustainability principles and objectives
.5 | Assess, use, and develop professional standards and tools for the program
.6 | Assess, benchmark, and improve the organization's program management competence
5.3.4 | Power and interest |  |  |  | 3 | 2
.1 | Assess the personal ambitions and interests of others and the potential impact of these on the program
.2 | Assess the informal influence of individuals and groups and its potential impact on the program
.3 | Assess the personalities and working styles of others and employ them to the benefit of the program
5.3.5 | Culture and values |  |  |  | 3 | 2
.1 | Assess the implication of culture and values of the relevant context
.2 | Align the program with the formal culture and values of the coordinating organizations
.3 | Assess the implications of informal culture and values of the coordinating organizations
Personal Competence Elements
5.4.1 | Self-reflection and self-management |  |  |  | 5 | 3
.1 | Identify, and reflect on, the ways in which one's own values and experiences affect the work
.2 | Build self-confidence on the basis of personal strengths and weaknesses
.3 | Identify, and reflect on, personal motivations to set personal goals and keep focus
.4 | Organize personal work depending on the situation and one's own resources
.5 | Take responsibility for personal learning and development
5.4.2 | Personal integrity and reliability |  |  |  | 5 | 3
.1 | Acknowledge and apply ethical values to all decisions and actions
.2 | Promote the sustainability of outputs and outcomes
.3 | Take responsibility for one's own decisions and actions
.4 | Act, take decisions, and communicate in a consistent way
.5 | Complete tasks thoroughly in order to build confidence with others
5.4.3 | Personal communication |  |  |  | 5 | 3
.1 | Provide clear and structured information to others and verify their understanding
.2 | Facilitate and promote open communication
.3 | Choose communication styles and channels to meet the needs of the audience, situation, and management level
.4 | Communicate effectively with virtual teams
.5 | Employ humor and sense of perspective when appropriate
5.4.4 | Relations and engagement |  |  |  | 5 | 3
.1 | Initiate and develop personal and professional relations
.2 | Build, facilitate, and contribute to social networks
.3 | Demonstrate empathy through listening, understanding, and support
.4 | Show confidence and respect by encouraging others to share their opinions or concerns
.5 | Share one's own vision and goals in order to gain the engagement and commitment of others
5.4.5 | Leadership |  |  |  | 5 | 3
.1 | Initiate actions and proactively offer help and advice
.2 | Take ownership and show commitment
.3 | Provide direction, coaching, and mentoring to guide and improve the work of individuals and teams
.4 | Exert appropriate power and influence over others to achieve program goals
.5 | Make, enforce, and review decisions
5.4.6 | Teamwork |  |  |  | 5 | 3
.1 | Select and build the team
.2 | Promote cooperation and networking between team members
.3 | Support, facilitate, and review the development of the team and its members
.4 | Empower teams by delegating tasks and responsibilities
.5 | Recognize errors to facilitate learning from mistakes
5.4.7 | Conflict and crisis |  |  |  | 4 | 2
.1 | Anticipate and possibly prevent conflicts and crises
.2 | Analyze the causes and consequences of conflicts and crises and select appropriate response(s)
.3 | Mediate and resolve conflicts and crises and/or their impact
.4 | Identify and share learning from conflicts and crises in order to improve future practice
5.4.8 | Resourcefulness |  |  |  | 5 | 3
.1 | Stimulate and support an open and creative environment
.2 | Apply conceptual thinking to define situations and strategies
.3 | Apply analytic techniques to analyzing situations and financial and organizational data and trends
.4 | Promote and apply creative techniques to find alternatives and solutions
.5 | Promote a holistic view of the program and its context to improve decision-making
5.4.9 | Negotiation |  |  |  | 5 | 3
.1 | Identify and analyze the interests of all parties involved in the negotiation
.2 | Develop and evaluate options and alternatives with the potential to meet the needs of all parties
.3 | Define a negotiation strategy in line with one's own objectives that is acceptable to all parties involved
.4 | Reach negotiated agreements with other parties that are in line with one's own objectives
.5 | Detect and exploit additional selling and acquisition possibilities
5.4.10 | Results orientation |  |  |  | 5 | 3
.1 | Evaluate all decisions and actions against their impact on program success and the objectives of the organization
.2 | Balance needs and means to optimize outcomes and success
.3 | Create and maintain a healthy, safe, and productive working environment
.4 | Promote and 'sell' the program and its processes and outcomes
.5 | Deliver results and get acceptance
Practice Competence Elements
5.5.1 | Program design |  |  |  | 8 | 4
.1 | Acknowledge, prioritize, and review success criteria
.2 | Review, apply, and exchange lessons learned from and with other programs and components
.3 | Determine complexity and its consequences for the approach
.4 | Create a program vision
.5 | Create and adapt a change strategy
.6 | Select and tailor the overall program management approach
.7 | Design the program execution architecture
.8 | Design a program delivery strategy
5.5.2 | Benefits and objectives |  |  |  | 5 | 3
.1 | Define and develop the goals and benefits hierarchy
.2 | Identify and (if possible) quantify the program benefits
.3 | Develop the benefits realization strategy
.4 | Define components, their outcomes, and their interfaces
.5 | Monitor benefit achievement
5.5.3 | Scope |  |  |  | 4 | 2
.1 | Define the program scope
.2 | Define the scope structure of the program
.3 | Manage the scope of the components
.4 | Establish and maintain scope configuration
5.5.4 | Time |  |  |  | 3 | 2
.1 | Sequence program components and create a tranched roadmap
.2 | Manage the consistency of the tranches
.3 | Manage the transitions of the tranches
5.5.5 | Organization and information |  |  |  | 4 | 2
.1 | Design and implement program governance framework and rules
.2 | Define the structure, roles, and responsibilities within the program
.3 | Establish infrastructure, processes, and systems for information flows
.4 | Implement, monitor, and maintain the organization of the program
5.5.6 | Quality |  |  |  | 2 | 1
.1 | Ensure quality throughout the program
.2 | Organize quality assurance of the program
5.5.7 | Finance |  |  |  | 5 | 3
.1 | Determine and establish the program budget
.2 | Determine the program funding and financing strategy
.3 | Develop, establish, and govern a funding and financial management framework
.4 | Distribute program funds based on the needs of components and funding conditions
.5 | Provide reports to funding and financing bodies
5.5.8 | Resources |  |  |  | 5 | 3
.1 | Develop a strategic resource plan to deliver the program
.2 | Define the quality and quantity of resources required
.3 | Identify the potential sources of resources, and negotiate their availability
.4 | Allocate and distribute resources according to defined need
.5 | Evaluate resource usage
5.5.9 | Procurement and partnership |  |  |  | 3 | 2
.1 | Maintain and govern the procurement system for the program
.2 | Develop partnerships
.3 | End partnerships
5.5.10 | Plan and control |  |  |  | 5 | 3
.1 | Establish the program
.2 | Measure and evaluate the status of components, and influence their progress
.3 | Manage the interfaces and synergies between components
.4 | Provide direction to the component managers
.5 | Finalize the program
5.5.11 | Risk and opportunity |  |  |  | 5 | 3
.1 | Develop and implement a risk management framework
.2 | Identify risks and opportunities
.3 | Assess the probability and impact of risks and opportunities
.4 | Select strategies and implement response plans to address risks and opportunities
.5 | Evaluate and monitor risks, opportunities, and implemented responses
5.5.12 | Stakeholders |  |  |  | 5 | 3
.1 | Identify stakeholders, and analyze their interests and influence
.2 | Develop and maintain a stakeholder strategy and communication plan
.3 | Engage with the executive, sponsors, and higher management to gain commitment and to manage interests and expectations
.4 | Engage with other stakeholders to gain their cooperation and commitment
.5 | Organize and maintain networks and alliances
5.5.13 | Change and transformation |  |  |  | 4 | 2
.1 | Assess the adaptability to change of the organization(s)
.2 | Identify change requirements and transformation opportunities
.3 | Develop change or transformation strategy
.4 | Implement change or transformation management strategy
5.5.14 | Select and balance |  |  |  | 4 | 2
.1 | Analyze the characteristics of components
.2 | Prioritize components based on the program's priorities
.3 | Analyze and predict the future performance of the program
.4 | Prepare and facilitate program decisions
Summary
| Perspective competence elements satisfied | 0
| Personal competence elements satisfied | 0
| Practice competence elements satisfied | 0
Overall result
| Required to pass | 24
version 4.1

## Portfolio Scores
| Detail Self-Assessment Portfolio Domain |  | Rate the level of your agreement with the following statement:
I can provide clear and convincing evidence of my Skills and Abilities
in the indicated KCI from a portfolio of sufficient complexity for the level applied for.
Blank = Disagree or no evidence; 1 = Neutral; 2 = Agree; 3 = Strongly agree
|  | S&A | Notes, comments, and evidence
Perspective Competence Elements
6.3.1 | Strategy |  |  | 5 | 3 | Converted spelling and punctuation to US English
.1 | Align with organizational mission and vision
.2 | Identify and exploit opportunities to influence organizational strategy
.3 | Develop and ensure the ongoing validity of the business/organizational justification
.4 | Determine, assess, and review critical success factors
.5 | Determine, assess, and review key performance indicators
6.3.2 | Governance, structures, and processes |  |  | 4 | 2
.1 | Know the principles of portfolio management and the way they are implemented
.2 | Align the portfolio with the organization's reporting and decision-making structures and quality management processes
.3 | Align the portfolio with the organization's human resource processes and functions
.4 | Align the portfolio with the organization's finance and control processes and functions
6.3.3 | Compliance, standards, and regulations |  |  | 6 | 3
.1 | Identify, and ensure that the portfolio complies with, all relevant legislation
.2 | Identify, and ensure that the portfolio complies with, all relevant health, safety, security, and environmental regulations (HSSE)
.3 | Identify, and ensure that the portfolio complies with, all relevant codes of conduct and professional regulation
.4 | Identify, and ensure that the portfolio complies with, relevant sustainability principles and objectives
.5 | Assess, use, and develop professional standards and tools for the portfolio
.6 | Assess, benchmark, and improve the organization's portfolio management competence
6.3.4 | Power and interest |  |  | 3 | 2
.1 | Assess the personal ambitions and interests of others and the potential impact of these on the portfolio
.2 | Assess the informal influence of individuals and groups and its potential impact on the portfolio
.3 | Assess the personalities and working styles of others and employ them to the benefit of the portfolio
6.3.5 | Culture and values |  |  | 3 | 2
.1 | Assess the culture and values of society and their implications for the portfolio
.2 | Align the portfolio with the formal culture and values of the organization
.3 | Assess the informal culture and values of the organization and their implications for the portfolio
Personal Competence Elements
6.4.1 | Self-reflection and self-management |  |  | 5 | 3
.1 | Identify, and reflect on, the ways in which one's own values and experiences affect the work
.2 | Build self-confidence on the basis of personal strengths and weaknesses
.3 | Identify, and reflect on, personal motivations to set personal goals and keep focus
.4 | Organize personal work depending on the situation and one's own resources
.5 | Take responsibility for personal learning and development
6.4.2 | Personal integrity and reliability |  |  | 5 | 3
.1 | Acknowledge and apply ethical values to all decisions and actions
.2 | Promote the sustainability of outputs and outcomes
.3 | Take responsibility for one's own decisions and actions
.4 | Act, take decisions, and communicate in a consistent way
.5 | Complete tasks thoroughly in order to build confidence with others
6.4.3 | Personal communication |  |  | 5 | 3
.1 | Provide clear and structured information to others and verify their understanding
.2 | Facilitate and promote open communication
.3 | Choose communication styles and channels to meet the needs of the audience, situation, and management level
.4 | Communicate effectively with virtual teams
.5 | Employ humor and sense of perspective when appropriate
6.4.4 | Relations and engagement |  |  | 5 | 3
.1 | Initiate and develop personal and professional relations
.2 | Build, facilitate, and contribute to social networks
.3 | Demonstrate empathy through listening, understanding, and support
.4 | Show confidence and respect by encouraging others to share their opinions or concerns
.5 | Share one's own vision and goals in order to gain the engagement and commitment of others
6.4.5 | Leadership |  |  | 5 | 3
.1 | Initiate actions and proactively offer help and advice
.2 | Take ownership and show commitment
.3 | Provide direction, coaching, and mentoring to guide and improve the work of individuals and teams
.4 | Exert appropriate power and influence over others to achieve program goals
.5 | Make, enforce, and review decisions
6.4.6 | Teamwork |  |  | 5 | 3
.1 | Select and build the team
.2 | Promote cooperation and networking between team members
.3 | Support, facilitate, and review the development of the team and its members
.4 | Empower teams by delegating tasks and responsibilities
.5 | Recognize errors to facilitate learning from mistakes
6.4.7 | Conflict and crisis |  |  | 4 | 2
.1 | Anticipate and possibly prevent conflicts and crises
.2 | Analyze the causes and consequences of conflicts and crises and select appropriate response(s)
.3 | Mediate and resolve conflicts and crises and/or their impact
.4 | Identify and share learning from conflicts and crises in order to improve future practice
6.4.8 | Resourcefulness |  |  | 5 | 3
.1 | Stimulate and support an open and creative environment
.2 | Apply conceptual thinking to define situations and strategies
.3 | Apply analytic techniques to analyzing situations and financial and organizational data and trends
.4 | Promote and apply creative techniques to find alternatives and solutions
.5 | Promote a holistic view of the program and its context to improve decision-making
6.4.9 | Negotiation |  |  | 5 | 3
.1 | Identify and analyze the interests of all parties involved in the negotiation
.2 | Develop and evaluate options and alternatives with the potential to meet the needs of all parties
.3 | Define a negotiation strategy in line with one's own objectives that is acceptable to all parties involved
.4 | Reach negotiated agreements with other parties that are in line with one's own objectives
.5 | Detect and exploit additional selling and acquisition possibilities
6.4.10 | Results orientation |  |  | 5 | 3
.1 | Evaluate all decisions and actions against their impact on portfolio success and the objectives of the organization
.2 | Balance needs and means to optimize outcomes and success
.3 | Create and maintain a healthy, safe, and productive working environment
.4 | Promote and 'sell' the portfolio and its processes and outcomes
.5 | Deliver results and get acceptance
Practice Competence Elements
6.5.1 | Portfolio design |  |  | 2 | 1
.1 | Acknowledge, prioritize, and review success criteria
.2 | Review, apply, and exchange lessons learned from and with other portfolios
6.5.2 | Benefits |  |  | 1 | 1
.1 | Define and develop the organizational goals and benefits hierarchy
6.5.3 | Scope |  |  | 2 | 1
.1 | Establish and maintain the scope of the portfolio
.2 | Control scope configuration of projects and programs
6.5.4 | Time |  |  | 1 | 1
.1 | Establish the portfolio decision-making cycle
6.5.5 | Organization and information |  |  | 4 | 2
.1 | Assess and determine the needs of stakeholders relating to information and documentation
.2 | Define the structure, roles, and responsibilities within the portfolio and component projects and programs
.3 | Establish infrastructure, processes, and systems for information flow
.4 | Implement, monitor, and maintain the organization of the portfolio and component projects and programs
6.5.6 | Quality |  |  | 1 | 1
.1 | Ensure quality throughout portfolio component projects and programs
6.5.7 | Finance |  |  | 3 | 2
.1 | Determine and establish the portfolio budget
.2 | Determine the program funding and financing strategy
.3 | Develop, establish, and govern a financial performance and reporting system for the portfolio
6.5.8 | Resources |  |  | 3 | 2
.1 | Develop a strategic resource plan to deliver portfolio component projects and programs
.2 | Identify the quantity of required and available resources for running portfolio component projects and programs
.3 | Identify the skills of the required resources for running portfolio component projects and programs
6.5.9 | Procurement and partnership |  |  | 1 | 1
.1 | Maintain and govern the procurement system for the portfolio
6.5.10 | Plan and control |  |  | 3 | 2
.1 | Establish the portfolio system
.2 | Report on the portfolio
.3 | Establish and maintain the portfolio cycle
6.5.11 | Risk and opportunity |  |  | 5 | 3
.1 | Develop and implement a risk management framework
.2 | Identify risks and opportunities
.3 | Assess the probability and impact of risks and opportunities
.4 | Select strategies and implement treatment plans to address risks and opportunities
.5 | Evaluate and monitor risks, opportunities, and implemented responses
6.5.12 | Stakeholders |  |  | 5 | 3
.1 | Identify stakeholders, and analyze their interests and influence
.2 | Develop and maintain a stakeholder strategy and communication plan
.3 | Engage with the executive, sponsors, and higher management to gain commitment and to manage interests and expectations
.4 | Engage with users, partners, and suppliers to gain their cooperation and commitment
.5 | Organize and maintain networks and alliances
6.5.13 | Change and transformation |  |  | 3 | 2
.1 | Assess and review the impacts of changes affecting the portfolio
.2 | Develop change or transformation strategy for the portfolio
.3 | Sustain the change process
6.5.14 | Select and balance |  |  | 6 | 3
.1 | Identify programs or projects or ideas that could be included in the portfolio
.2 | Analyze the characteristics of programs and projects
.3 | Prioritize programs and projects based on the organization's priorities
.4 | Analyze and predict the future performance of a portfolio
.5 | Prepare and facilitate portfolio decisions
.6 | Provide program and project delivery oversight
Summary
| Perspective competence elements satisfied | 0
| Personal competence elements satisfied | 0
| Practice competence elements satisfied | 0
Overall result
| Required to pass | 24
version 4.1